## Sheet1
[9 empty] | 2026-02-02 | [12 empty] | 2026-05-04 | [12 empty] | 2026-08-03 | [12 empty] | 2026-11-02 | [12 empty] | 2027-02-01 | [12 empty] | 2027-05-03 | [12 empty] | 2027-08-02 | [12 empty] | 2027-11-01
|  | Project Start Date: | 2025-12-29 | [5 empty] | 2026-01-05 |  |  |  | 2026-02-02 |  |  |  | 2026-03-02 |  |  |  |  | 2026-04-06 |  |  |  | 2026-05-04 |  |  |  | 2026-06-01 |  |  |  |  | 2026-07-06 |  |  |  | 2026-08-03 |  |  |  | 2026-08-31 |  |  |  |  | 2026-10-05 |  |  |  | 2026-11-02 |  |  |  | 2026-11-30 |  |  |  |  | 2027-01-04 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  |  | 2027-04-05 |  |  |  | 2027-05-03 |  |  |  | 2027-05-31 |  |  |  |  | 2027-07-05 |  |  |  | 2027-08-02 |  |  |  | 2027-08-30 |  |  |  |  | 2027-10-04 |  |  |  | 2027-11-01 |  |  |  | 2027-11-29 |  |  |  |  | 2028-01-03
|  | Project Name: | Enter your project name |  |  |  |  | Week Starting | time axis 2025-12-29 to 2028-01-17
| # | Activity | Assigned To | Start | End | Days | Status | % Done
v | 1 | Overall Project - Clean house | Everyone | 2026-01-01 | 2026-12-31 | 261 | In Progress | 85% | bar: 2026-12-28
u | 2 | Clean bathroom | Red Team | 2026-01-30 | 2026-12-10 | 225 | Blocked | 60% | bar: 2026-12-07
w |  | Clean Tub | John | 2026-02-07 | 2026-03-16 | 26 | Not Started | 40% | bar: 2026-03-16
w |  | Clean Toilet | Bob | 2026-01-16 | 2026-03-19 | 45 | Blocked | 90% | bar: 2026-03-16
w |  | Clean Shower Curtain | James | 2026-11-07 | 2026-12-05 | 20 | In Progress | 10% | bar: 2026-12-07
w |  | Clean Mirror | Kate | 2026-01-07 | 2026-06-15 | 114 | Complete | 100% | bar: 2026-06-15
u | 3 | Clean Living Room | Blue Team | 2026-01-01 | 2026-02-28 | 42 | bar: 2026-03-02
w |  | Vacuum | Mike | 2026-01-07 | 2026-03-15 | 48 | Not Started | 50% | bar: 2026-03-16
w |  | Dust | Anna | 2026-01-07 | 2026-03-15 | 48 | Not Started | 40% | bar: 2026-03-16
o |  | Clean Couch | Peter | 2026-01-07 | 2026-04-15 | 71 | Not Started | 32% | bar: 2026-04-13
w |  | Mop | George | 2026-01-07 | 2026-03-19 | 52 | Not Started | 10% | bar: 2026-03-16
u | 4 | Clean Kitchen | Red Team | 2026-03-26 | 2026-08-31 | 52 | Not Started | 10% | bar: 2026-08-31
w |  | Mop Floor | Some other dude | 2026-03-26 | 2026-04-30 | 26 | Not Started | 10.5% | bar: 2026-04-27
w |  | Wipe Counters | Not Me | 2026-04-04 | 2026-05-20 | 33 | Not Started | 20% | bar: 2026-05-18
w |  | Clean Fridge
w |  | Throw out old food
w |  | Sautee onions
w |  | Wash Dishes
u |  | Main Task 4
w |  | Task 17
w |  | Task 18
w |  | Task 19
w |  | Task 20
w |  | Task 21
w |  | Task 22
w |  | Task 23
w |  | Task 24
w |  | Task 25
w |  | Task 26
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))

## Settings
Statuses | Icons
Not Started
In Progress | u
Blocked | v
Complete | w
o